## Slide 1: Capstone Project

## Slide 2: Team 1
Rohit
Kiran
Nayanthara
Nimisha
Rijo
Ishani Mariya Mathew
Sintu Mathew Koshy

## Slide 3: Instructions
All team members are advised to participate in project.
There will be team leaders for project, and it doesn’t mean that its his/her responsibility to fulfill the project requirements.
The project will be tracked by Scrum methodology.
Project updates must be pushed into the project repositories by Team members themselves(Will be assigned later)
If any participant is not partaking in project responsibilities , Team lead/other participants must inform the same to the project managers (Leena/Titto).
Non-participation in projects will not be tolerated, and it may impact internship certification.
All team members must attend project meetings as scheduled for effective communication and collaboration

## Slide 4
Datasets
Domain : Movies and Genre
Project Name: Recommendation System
Dataset Name: movies.xls
Dataset Type: Excel Data
Dataset Size: 9742 records each

## Slide 5: COMPLETE PROJECT PLAN
Date | Itinerary | Final Date for Execution/presentation | Stream
08/12/2023 | Dataset(I) will be Shared to DA for initial cleaning and visualization | 15/12/2023 | DA
15/12/2023 | Dataset(I) and primary reports will be handed over to DS for further Analysis(Regression , Prediction ..) | 29/12/2023 | DS
 | New Datasets(II) will be given to DA for visualization in tools other than the tool used for Dataset(I) | 29/12/2023 | DA
29/12/2023 | DA & DS collectively draw conclusions from Dataset(I) and prepare a ppt with their insights and present it | 03/01/2024 | DA&DS

## Slide 6: DA Responsibilities
DATA ANALYST PROJECT PLAN |  | 
Date | Itinerary | Final Date for Execution/presentation
08/12/2023 | Dataset(I) will be Shared to DA for initial cleaning and visualization | 15/12/2023
15/12/2023 | New Datasets(II) will be given to DA for visualization in tools other than the tool used for Dataset(I) Work out the Tasks for Dataset(II) in the Secondary group formed for Visualization project | NB: Dataset(II), Team Details and instruction ppt will be sent separately to Participants Mail_id.
 | Visualization/KPI Presentation of Dataset (II) in Excel and SQL. | 22/12/2023
 | Visualize the KPIs and Dashboard in Power BI/SQL | 26/12/2023
26/12/2023 | DA & DS collectively draw conclusions from Dataset(I) and prepare a ppt with their insights and present it | 03/01/2023

## Slide 7: DS Responsibilities
DATA SCIENCE PROJECT PLAN |  | 
Date | Itinerary | Final Date for Execution/presentation
12/15/2023 | Apply EDA on the dataset handed-over by the DA team | 12/18/2023
12/18/2023 | Create data models for the dataset using multiple algorithms and select the model with the highest accuracy or lowest error rate | 12/22/2023
12/22/2023 | Improve the quality of the model by applying optimization techniques. | 12/26/2023
12/26/2023 | Hand-over the drawn conclusions to the DA team to visualize the insights. | 1/3/2024
12/26/2023 | Deploy the Machine Learning Model using Flask or Streamlit | 1/3/2024